Five Year State Plan Development Timeline

1.	February to November, 2020 –

Needs Assessment Data – gather/review/analyze needs assessment/gaps in services/state agency system data.

- Seek data from the DD Network partners.

- Review needs data from past 3 years of Partners surveys.

- Review gaps in services data from Council member survey.

- Review Family Support satisfaction and needs data.

- Review Disability Pathfinder most requested services data.

- Review 2019/2020 UT economic report.

- Review most recent Compendium Statistical Report for TN.

- Review THDA Housing report for TN (2019/2020).

- Review data from PPRs and state plan updates.

- Review statistical data for TN (e.g., national data sets).

- Review most recent TCCY Kids Count report.

- Review state agency and key community partner state plans or planning documents.

2.	February, 2020 Council meeting –

- Present initial information about new state plan and timeline to the Council members.

- Continue developing state agency survey.

3.	March, 2020 –

- Email Council members public input survey for review/ comment.

3.	April, 2020 –

- Finalize public input survey, and state agency survey

4.	May, 2020 -

- May Council meeting - Council members complete final version of public input survey.

- Share any additional preliminary information about the new five year state plan.

- Share an update on progress on the needs assessment at the Council Meeting.

5.	June, 2020 –

- Finalize details for 60 days of public input, includes communications plan for distribution

6.	July, 2020 –

- Launch 60 days of public input.

7.	August, 2020

- Disseminate State Agency surveys

- Begin to draft preliminary, possible goals and objectives.

8.	September Council meeting –

- Provide update on writing CRA and needs assessment progress to Council members and receive their feedback.

9.	October, 2020 -

- Organize needs assessment data for use in the CR&A.

- Next draft of goals and objectives.

- Continue writing and editing various components of new plan.

- Receive and analyze state agency survey data.

7.	November, 2020 Council Retreat -

- Present final needs assessment data to Council members at Retreat.

- Present next draft version of Section IV goals and objectives of the state plan to Executive Committee and Council members for their feedback.

8.	December/January, 2020

- Make final edits recommended by Council members

- Prepare goals and objectives for 60 days of public review.

8. 	February, 2021 –

- No later than February 1, post state plan for 60 days of public review.

- Remind Council members that goals and objectives are posted for public review and to please share widely.

12.	April, 2021 –

- Work on the Assurances.

- Review comments received during public review, and develop recommended edits for Council review.

14.	May, 2021 Council meeting –

- Council members review comments and staff recommendations to decide what revisions are needed, resulting in last changes being finalized to new state plan.

- Council members then provide final approval of new State Plan at Council meeting.

16.	June - August 15, 2021

- Complete all remaining components of state plan.

- Enter new state plan and FY work plans into ACL on-line system.

17.	August 15, 2021 –

- State Plan submitted to OIDD.