State Plan Timeline – Key Dates

February thru November, 2020 - Needs assessment data is collected from three sources:

- Stakeholder partner agencies share with the Council their state plans and needs assessment data they have collected

- Public input survey:

  - March, 2020 - Council member review of survey draft

  - May, 2020 – Council members complete final version of survey during the Council meeting

  - July, 2020 - General public input sought for 60 days

- State agency survey: state agencies respond to a set of questions about the existing services.

September thru November, 2020 – Council staff use data collected and analyzed from needs assessment to develop drafts of the new proposed state plan:

- Goals and objectives,

- Logic model, and

- Evaluation plan

November, 2020 Retreat – Review with Executive Committee and Council the:

- Results of needs assessment data, and

- Draft of the proposed new State Plan goals and objectives

February, 2021 – Post proposed new State Plan goals and objectives for 60 days of public review

May, 2021 – Items for Council meeting:

- Present summary of public review comments,

- Review and discuss proposed final new State Plan goals and objectives, and

- Complete process for approval of new State Plan goals and objectives by Council

June thru August, 2021 – Last tasks before due date:

- Finalize last components of the new 5 year state plan (for example, proposed budget, assurances, rationale for goal selection), and

- Enter new state plan into federal reporting system

August 15, 2021 – New state plan submitted to Office of Intellectual and Developmental Disabilities