# Self Determination Milestones

# (along the Yellow Brick Road)

2001

February	Letter of invitation out from Council to participate in a Task Force on Self Determination (SDTF 1)

March	First Self Determination Task Force has its initial meeting; Human Services Research Institute (HSRI) provides consultation

May		Mission, Values & Guiding Principles developed by SDTF 1

July 	Negotiations between DHW & Council regarding roll out of utilization management (Region 2 pilot) and self-determination

September	Strategic Plan developed by SDTF 1

November	Final Meeting of the Initial SD Task Force

December	Presentation by SD Task Force to policy makers

2002

January	“Is There Another Way?” presentation on self-determination to the Legislature by Council

July	Technical assistance info gathered at national meetings

September	Interviews conducted with consumers in Region 2 using the

## Consumer Satisfaction instrument developed by Task Force

October	Council presentation on Self-Determination to Health & Human

## Services Committee of 2020 Task Force

November	HHS/2020 Committee recommends Self-Determination (in combination with Utilization Management) to the full 2020 Task Force

2003

March	Resolution passed encouraging Council to reconvene SDTF and

develop an SD pilot for 200 adults with DD using the components of an Independence Plus Waiver

May 	First meeting of Second Self-Determination Task Force (SDTF Waiver Project); subcommittees formed

June 		2020 Task Force includes Self-Determination among its final

recommendations to Governor

July	Independence Plus grant submitted to CMS by Medicaid in partnership with Council

August 	Second meeting of SDTF 2; design work continues in subcommittees

September	Drafting Committee formed of reps from all subcommittees

October 	Independence Plus Grant awarded

Consumer Education training begins for teams in Regions 1 & 7 with consultation from HSRI; beginning of Idaho Self Advocate Leadership Network (SALN)

2004

January 	Presentation to the Legislature by SALN Teams 1 and 7

February	Presentation made to the House Health & Welfare Committee

by SDTF members

March	Report given to Senate Health & Welfare Committee by SDTF

End of Consumer Ed training for Regions 1 & 7 SALN teams

Presentation by SALN and SDTF parents to IPUL conference

SDTF members attend CMS conference in Baltimore for technical assistance

April	Presentation made on SDTF work to Best of West Conference in Seattle

SALN presentations to consumers in Coeur d’Alene and Idaho Falls

Presentation made on SDTF work to Idaho Association of Developmental Disability Agencies state conference

May	Recruitment begins for Consumer Ed training teams in Regions 2, 5, 6

Presentation made on SDTF work to national Self Advocates Becoming Empowered (SABE) meeting

June	Presentation on self-determination in Idaho made to National Association of Councils on Developmental Disabilities Technical Assistance conference

Preliminary meetings with the Center on Disabilities and Human Development at the U of I to develop curriculum for support broker training

July 	Planning Summit for full SDTF; wrap up of design phase

SALN presentations to consumers in Sandpoint and Salmon

August	Drafting Committee review of Planning Summit recommendations; outline next steps

CMS Grant Monitoring call

Consumer Education training begins for SALN Teams for 
Regions 2, 5 and 6

September	SALN presentation to self-advocates and parents at the Idaho Partners Institute.

SALN presentations in Bonners Ferry, Ashton and Rexburg

October	SALN presentation at Council for Exceptional Children conference

SALN presentation to service providers and consumers at Community Partnerships of Idaho conference

November	Election Day

Begin contacting/meeting with legislators

2005

January 	Begin work on legislative approval

March	Begin recruiting support brokers

Receive legislative approval

Submit waiver amendment to CMS

April	Release RFP for Fiscal Employer Agency(ies)

May	Potential early CMS approval

Start to train and enroll support brokers

June 	Identify potential consumers for waiver; provide training with consumer tool-kit

2-5-6 SALN members graduate from leadership development training

Final waiver approval

July 		Prepare for implementation

SALN SUMMIT Teams 1, 2, 5, 6, and 7 for statewide team

development and to write mission statement and strategic plan

July	Conduct educational bus tour throughout Idaho, culminating with a rally at the State Capitol

August	Begin implementation

September	Begin ongoing evaluation

Modify system components as determined necessary

Recruitment of SALN members for Regions 3 and 4 and members to replace self-advocates in Regions 1 and 2

December	Leadership development training begins for Regions 3-4 and new members form Regions 1 and 2

2006

January	Report to Legislature

June	Regions 3-4 and new members from Region 1 and 2 graduate from SALN

##### October	Regions 2, 4, and 6 Regional Medicaid staff and Regional SALN Teams meet for train-the-trainer to begin training waiver participants in those regions

Ongoing Evaluation and Modification through Quality Assurance Measures

# Text boxes

TIME			ACTIVITY/PRODUCTS

### PLANNING PHASE

#### DESIGN PHASE

### DESIGN PHASE

#### CONSTRUCTION PHASE

###### IMPLEMENTATION

### EVALUATION AND MODIFICATION

#### CONSTRUCTION PHASE